## Start of Sprint - Amazing Softw
Mighty Morphin Mattew Rangers :: Sprint 1
User Story | Estimated Complexity | Done? | Tasks | Owner | Estimated Effort (Person hours) | Mon | Tue | Wed | Thu | Fri
1. Create Data Base to store app data: | 7 | N | Connect Database | Ryan,Douglas | 3 | 3 | 3 | 3 | 3 | 3
|  |  | Store data on exams | Ryan,Douglas | 2 | 4 | 4 | 4 | 4 | 4
2. Create Web Site | 3 | N | Front Page | Steven, Andy, Keiren | 10 | 10 | 10 | 10 | 10 | 10
|  |  | Login | Steven, Andy, Keiren | 6 | 6 | 6 | 6 | 6 | 6
|  |  | Display Exams | Steven, Andy, Keiren | 5 | 5 | 5 | 5 | 5 | 5
3. Upload Files | 7 | N | Browse Local files
Select pdf/wrd file
|  |  | Save file to database |  | 6
4. Display Current Stage | 5 | N | Retrieve Data from database
Display Exams
Display Stage
5. Comment on Exams | 5 | N | Store Comments in data base
Send Comments to data base
6. Create New Exam |  | N | Request data from user
Select pdf/wrd file
|  |  | Save file to database |  | 6
[6 empty] | Not started | In progress | Completed
Estimated velocity | 27 |  |  | Effort remaining | 26 | 28 | 28 | 28 | 28 | 28
Actual velocity | 0