## Group 7 Sprint 1
Group 7 : Sprint 1
User Story | Estimated Complexity | Done? | Tasks | Owner | Estimated Effort (Person hours) | Mon | Tue | Wed | Thu | Fri
1. Create Data Base to store app data: | 7 | N | Connect Database | Ryan,Douglas | 2
|  |  | Store data on exams | Ryan,Douglas | 3
2. Create Web Site | 3 | N | Front Page | Steven, Andy, Keiren
|  |  | Login | Steven, Andy, Keiren
|  |  | Display Exams | Steven, Andy, Keiren
3. Upload Files | 7 | N | Browse Local files | Matt, Declane
|  |  | Select pdf/wrd file | Matt, Declane
|  |  | Save file to database | Matt, Declane
4. Display Current Stage | 5 | N | Retrieve Data from database | Steven, Andy, Keiren
|  |  | Display Exams | Steven, Andy, Keiren
|  |  | Display Stage | Steven, Andy, Keiren
5. Comment on Exams | 5 | N | Store Comments in data base | Ryan, Douglas
|  |  | Send Comments to data base | Ryan, Douglas
6. Create New Exam | 6 | N | Request data from user | Matt, Declane
|  |  | Select pdf/wrd file | Matt, Declane
|  |  | Save file to database | Matt, Declane
[6 empty] | Not started | In progress | Completed
Estimated velocity | 33 |  |  | Effort remaining | 0 | 0 | 0 | 0 | 0 | 0
Actual velocity | 0